## Sheet1
Week/Day | Progress Made | Work Remaining
Summer 2014 |  | UI | New Features
Week 1 | CS 193P Lectures 1-3, Matchismo, MPMusicPlayerController notifications | No "done" button in mobile verification keypad | App invites
Week 2 | CS 193P Lectures 4-8, downloaded/configured Echoprint, tried to record with headset in | Link sent to self should also go to Received tab | Other audio/video content sources
|  | Change text message link to website URL | Send what I'm listening to
Tuesday (6/10) | Coded timers/automatic sampling, tried to resolve subproject errors (SongDetection EP) | Change received vs. sent tab bar colors | Favorite links
Wednesday (6/11) | Built UI, 12 second cyclic sampling for song ID | Scrolling autocomplete results hides keyboard | Deleting links and friend requests
Thursday (6/12) | Improved UI, song ID access in message VC | Fix searchResultsVC table frame/animation (iOS 8) | User point system - gold, silver, bronze
Friday (6/13) | Web view, Lecture 11 (Table View), tried using table views without table view VC | Highlight Send Link button label on click
Saturday (6/14) | Lecture 11 (Demo), table view/VC, embedded YT player, researched search APIs | Change iOS 8 watch symbol | Big Ideas
Sunday (6/15) | Researched search APIs, keyboard dismiss, tried to resolve GTL static lib errors | Continue playing audio in BG w/o interruption | Web page (news articles) links
Monday (6/16) | Resolved GTL static lib errors, YouTube title + artist search | Clicking Inbox tab should switch seg w/new push | Web-mobile sync
FriendsVC: add segmented control
Tuesday (6/17) | YT search filtering, New Link! buttons, UIWebView scaling | FriendsVC: display "no friend requests", etc.
Wednesday (6/18) | Sending, receiving, displaying song title/artist (JSON) info using 3rd party web server | Remove blank messages
Thursday (6/19) | Researched server solutions, setup Parse + FB SDK, tried to add login/sign up VCs | Disable web access through UIWebView
Friday (6/20) | Resolved login/sign up VC issue (MainWindow.xib), message storage + retrieval in Parse
Saturday (6/21) | Tried to display FB/Twitter login fields | Bugs/Errors | Performance
Sunday (6/22) | Lecture 10 (Multithreading), moved song ID to another thread, improved "Try Again" button | Reset numberPushRequests on app deletion | UI is sometimes blocked on app launch
Monday (6/23) | Tried to configure login w/FB, studied Parse sample code (login demo, integrating FB, AnyPic) | Rapid dismissal of pushNotifVC | Using file system cache to improve link load time
|  | Logout freeze on 64+ thread limit | Test whether UIImage imageWithData blocks UI
Tuesday (6/24) | Enabled FB/Twitter login fields, set login screen logo, tried to configure login w/FB | Refresh expired FB access tokens | InboxVC paging
Wednesday (6/25) | "Welcome" view, existing accounts logic, tried to link FB and LMU accounts (PFFacebookUtils) | Atypical usernames absent from contactsVC
Thursday (6/26) | Existing accounts logic, tried to retrieve FB friends list | Friends VC search: bug w/ accepted request | Benchmarking
Friday (6/27) | Resolved ObjC/C++ compile setting issue, retrieve/display FB friends in "Friends" tab | Simultaneous friend requests | Test performance of Parse with 1-10K active users
Saturday (6/28) | FriendRequest class, requests and suggestions in "Friends" tab | UIWebView autoplay failures | Consider alternative backend stacks
Sunday (6/29) | Current friends, accepting requests/updating current friends, removed redundant suggestions | Duplicate contents in self.userSearchContacts
Monday (6/30) | Link class, contacts VC tableview, selecting recipients of link, retrieving inbox of messages | Duplicate cell contents (addSubview) | Settings/Privacy
|  | CFNetwork SSLHandshake failed (-9806) | Don’t save address book to Parse
Tuesday (7/1) | PFRelation received links query, displaying sender/receiver information | Parse Errors (Code 1, -1011) | Update Privacy Policy / Terms in app
Wednesday (7/2) | Created constants.h file, Lecture 16 (Modal Segues + Text), tab bar and navigation controllers | Web thread crash
Thursday (7/3) | Resolved premature link creation, separated sent/received links with UISegmentedControl
Friday (7/4) | Setting seg control before inbox launch, researched alternatives to YouTube | Marketing/Promotion | Android Development
Saturday (7/5) | YouTube search filters to remove unplayable + undesirable videos | Get email list from ExactData | Go through iOS code to determine min feature set
Sunday (7/6) | Fixed login with FB, tried to record with headset, "link with facebook" button | Promote contest (FB ads, etc) | Get Android icon/launch screens produced
Monday (7/7) | Data model, load app data on app launch, refresh data on ViewWillAppear | Buy appshout! Noise package | Go through (recent) Android code
|  | Post on Product Hunt, Reddit, HN | Look into alpha/beta testing procedures
Tuesday (7/8) | Resolved contacts VC issue (reusing cells), added UIRefreshControl functionality | Get video produced for YouTube ad | Prepare for launch
Wednesday (7/9) | Player/recorder delegate methods, experimented with title/artist text fields | Advertise on Pinterest, Tumblr, Pandora
Thursday (7/10) | Options VC (user enter/song ID)
Friday (7/11) | Album art through iTunes, title/artist text fields, song info VC | Website | Logging and Analytics
Saturday (7/12) | Linked options/info VCs to contacts VC, sending/retrieving album art, activity indicator | Center App Store / Google Play Store badges | Find source of current App Store traffic
Sunday (7/13) | Replaced ints with typdef enums, researched dispatch_apply | Add icon to website logo | Write analytics suite to analyze existing data
Monday (7/14) | Loading art async, data model refresh w/inst vars, Twilio SMS confirmation | Test site on different browsers - IE, mobile | More logging (crashes, Parse/iOS NSLogs)
|  | Properly configure meta OG share image | Configure Google Analytics + FB Pixel
Tuesday (7/15) | Completed SMS identity confirmation, annotation text view | Add/optimize meta keywords | Use Parse Analytics to track events/crashes
Wednesday (7/16) | Annotation content animation, received annotations, resolved inbox data crashes | Display Vimeo video on mobile | More complete error handling code
Thursday (7/17) | Default messenger state, subclassed Link table cells, Link date label, YT results scoring system | Minify CSS and JS
Friday (7/18) | YT results scoring system, researched patents and ownership | Use CloudFront or other CDNs to speed up site | Code Organization
Saturday (7/19) | NDA forms, table view + toolbar in link VC | Fix spacing/padding of social icons | Update Parse/FB Frameworks
Sunday (7/20) | Link VC toolbar, reply VC, receiversData field, receiversData seen state | Add "Made in Seattle, WA" to footer | Test LMU app build on another computer
Monday (7/21) | Added date stamp to messages, entering/scrolling/posting in reply VC | Make iPhone/text larger at each screen size | Regroup and rename classes in project
|  | Improve wrapping behavior of tagline | Remove trunk/Example and build/
Tuesday (7/22) | Subclassed link VC (sent/received link VCs), added messages below YT video | Switch to AWS Route 53 for DNS services | Remove unused frameworks
Wednesday (7/23) | Sorted sent VC messages, Friends tab search bar, data refresh bug, organized code
Thursday (7/24) | Organized code, friending non-FB friends, refresh controls, link time stamps | Expenses | Coding Style / Conventions
Friday (7/25) | Link time stamps, link ordering/status, fixed webview scroll issue | iOS Developers Account - $99 (x2) | Declare dictionary keys as constants
Saturday (7/26) | SSL Certificate for push notifs | Toolbar Icons - $25 | Replace #define macros with constants
Sunday (7/27) | Provisioning Profile, Parse push notifs setup | App Icon (IconShock) - $20 | Replace IS_IPHONE5 with new IS_IPHONE_5
Monday (7/28) | Accept request bug, Link push notifs (background state) | iPhone 5 Restocking Fee - $35 (x2) | Replace setObj, objForKey, initWithObjs w/literals
|  | Twilio - $20 | Hold song/video data in NSDictionary (subclass?)
Tuesday (7/29) | Eliminated VWA refresh, push notifs (links, messages, requests), tab bar badges | GoDaddy - $14.42 | Move loadUpdatedLink, etc. to superclass
Wednesday (7/30) | Badge updates, push notifs (sent requests), researched YT search bar API | Weebly Starter Plan - $49 (x1) | Move local data update functions to data model (?)
Thursday (7/31) | YT autocomplete API, YT search bar with autocomplete suggestions | LLC Registration Fees - $200 + DOR Fee
Friday (8/1) | YT video search results for query, YT embedded videos | Weebly Domain - $40 (x1) | Hacks/Patches
Saturday (8/2) | Horizontal table view, UIWebView array with captions, isSong field, sending/displaying videos | Startup Career Fair - $46 (taxi) + $100 (fee) | Settings icon background
Sunday (8/3) | Emailed icon designers, video annotation, Lecture 12 (Core Data), tried UINavBar | Launch Screen (IconShock) - $7 | Bar button positioning in Xib files
Monday (8/4) | Search VC (song/video search), replaced ASIHTTP, tried local art caching | Photoshop - $120 | Use of device/OS macros
|  | Google Apps - $5 (x1) | GTL YouTube API deprecations patched
Tuesday (8/5) | 200x200 art, emailed designers, video thumbnails, enabled song info VC | Call to Action (IconShock) - $3 | searchResultsVC - separate VC for iOS 8
Wednesday (8/6) | Added toolbar icons, customized YT search bar, back buttons, "sent to" field, play icon | Vimeo Video Hosting - $10 (x1) | Inclusion of app icon through Info.plist
Thursday (8/7) | Play button, tried filtering by YT restrictions, YT thumbnail a.i., tried webview autoplay | Android Development - $2250 | NSDictionary cast for Youtube metadata
Friday (8/8) | Like/love buttons, added VEVO results, link a.i. bug, resolved r.c freezing, researched autoplay | Facebook Ads - $119.61
Saturday (8/9) | Emailed designers, memory usage test | Google Play Registration Fee - $25
Sunday (8/10) | Link fetch before update, expanded receiversData, like/love with push notifs
Monday (8/11) | Resolved link action update issues, link VC fetch on load, tried thin text fields | Apple Enrollment ID: 6YQKU4DGAD
D-U-N-S Number: 079635815
Tuesday (8/12) | Tried webview autoplay, link forwarding, link update bug, search VC bars enabled | D-U-N-S ID Number 102122-149236
Wednesday (8/13) | Reusing art on reload, toolbar icon captions, deleted video bug
Thursday (8/14) | iTunes badge | Blue - met with friends
Friday (8/15) | Toolbar spacing, iTunes badge w/link | Red - went out with family
Saturday (8/16) | Adjusted toolbar, settings icon + VC, log out action sheet | Purple - travel
Sunday (8/17) | Log out and push notif logic, resolved log out crashes, sent link toolbar, welcome label bug
Monday (8/18) | Like/love time info + VC, organized code, contacts VC bug, push notifs states
Tuesday (8/19) | Periodic data updates, data/memory usage tests, link VC song header, iTunes cell
Wednesday (8/20) | Moved iTunes cell, preview/available labels, streaming with AVPlayer
Thursday (8/21) | Preview play/pause buttons, reply VC title, reply VC header
Friday (8/22) | Reply VC header, replaced parallel link/art/contact arrays, local data variables
Saturday (8/23) | Sent/rec link update queue, reorg friends data update methods, push notif bug
Sunday (8/24) | Autocomplete behavior, 5 account limit
Monday (8/25) | Tried autoplay, VC transitions, art aspect fit, launch w/push notif, switch UISeg w/click on tab
Tuesday (8/26) | Tried autoplay, UISearchBar behavior, closed verification flow loophole
Wednesday (8/27) | UIWebView autoplay, memory warning response, reorg friends data update methods
Thursday (8/28) | Transferred Echoprint project, organized image files, removed echoprint dependencies
Friday (8/29) | Readded Pods subproj, renamed project/scheme, provisioning profile, prepackaged songs
Saturday (8/30) | Song search behavior, update timer bug, set up iPhone 5s, XIB files autolayout
Sunday (8/31) | Lecture 9 (Autolayout), NSLayoutConstraints, reply VC iPhone 5 animation offsets
Monday (9/1) | Master account, downloading master links, tried video table autolayout
Tuesday (9/2) | Song/video VC iPhone 5 layout, tried myLogIn iPhone 5 layout, terms of use + privacy policy
Wednesday (9/3) | Credits, submission process, domain names, screenshots, removed starred, reachability
Thursday (9/4) | Network alerts, art + contacts VC bug, screenshots, tried logging autoplay status, legal info label
Friday (9/5) | myLogIn layout, send SMS again label, legal info label, enabled Twilio, asset catalog
Saturday (9/6) | App description, myLogin/Signup layout, LinkMeUp push certificate, uploaded archive 1.0.0
Sunday (9/7) | Flight to Princeton, NJ
Monday (9/8) | App keywords, uploaded archive 1.1
Tuesday (9/9) | Logout freezing bug, uploaded + submitted archive 1.1.5, researched invalid binary issue
Wednesday (9/10)
Thursday (9/11)
Friday (9/12) | Submitted archive 1.2 w/app loader
Sept 23 - Oct 11 | Update to Xcode 6, handled iOS 8 deprecations (GTL, constants, push notifs)
Wednesday (10/1) | GTL static lib iOS 8 updates
Saturday (10/11) | Tested on iOS 8 simulator
Fall Break
Monday (10/27) | Updated to Xcode 6.1, tested on iOS8/iPhone 5s device
Tuesday (10/28) | Tried fixing horizontal table frame in searchResults VC
Wednesday (10/29) | Horizontal table frame + animation, renamed icons for iOS 8, investigated logout freeze issue
Thursday (10/30) | FB and Parse iOS 8 SDKs, submitted archive 1.3
Sunday (11/2) | Fixed checkmark icon iOS 8 size issue
Friday (11/7) | First version live in App Store
Sunday (11/9) | Replaced setObjectForKey with literals
Sunday (11/16) | Investigated App Store crashes, traced crash logs on device
Wednesday (11/19) | Used VideoSnippet title in searchResults VC; adjusted legal info position; submitted archive 1.45
Thanksgiving Break
Tuesday (11/25) | Tried changing Google Dev. Console API settings
Wednesday (11/26) | Investigated non-public selectors warning
Thursday (11/27) | Used JSON fields for GTL video metadata; submitted archive 1.50
Sunday (11/30) | Applied for D-U-N-S number
Tuesday (12/2) | Talked to D&B rep; used NSDictionary cast for GTL thumbnails; submitted archive 1.60
Sunday (12/7) | Tested audio issue on iPhone 6; enabled audio on Silent setting; submitted archive 1.70
Winter Break
Sunday (12/14) | Added "find friends" to signup flow; created linkWithFB VC; registered as LLC with SoS
Monday (12/15) | Case insensitive user search
Wednesday (12/17) | Link with FB button; skip option; submitted archive 1.80
Sunday (12/21) | Created FB page; sent LLC certificate to D&B
Intersession
Sunday (1/25) | Researched Address Book; investigated Friends VC friend request bug
Wednesday (1/28) | Wrote Princeton CS Group Page pitch
Semester 2
Saturday (2/7) | Wrote Summer 2015 desired roles description
Friday (2/20) | Represented LMU at HireTigers Startup Meetup
Saturday (2/21) | Contacted Android and web developer candidates; started eLab application
Sunday (3/8) | Started letter to Sarang
Thursday (3/12) | Finished and sent letter to Sarang
Tuesday (3/17) | Met with Devansh
Saturday (4/3) | Met with Henry Stolz
Thursday (4/9) | Interviewed Henry
Summer 2015
Week 1 | Put app on git/github; importing AB contacts; friend suggestions; alphabetizing contactsVC
Week 2 | ContactsVC - sending texts to non-users, Recents section, icons and UI; LinkedIn inMail
Week 3 | Scrollable button label; push notif/AB permissions flow; interv. Calvin; posted to FB groups
Week 4 | Changed searchVC UI; new launch screens; general debugging/testing; interv. Sean
Week 5 | Master links; screenshots; offer/contract for Sean; submitted archive; created app video
Week 6 | Finalized video; helped Sean; created press kit; emails to 19 journalists (+7 review sites)
Week 7 | Landing page; Facebook ads; app launch - FB posts and PMs; v2.05 screenshots; AB crash
Week 8 | Signup flow bug; PR agencies; YouTube stars; CPI/CPC FB ads; v2.10 screenshots
Week 9 | Posting on PH/HN; int'l phone # verif; planned/ran contest; contestDrawing.py; started v2.15
Week 10 | Server logging; FB signup issue; new website - AWS S3, Endless' code, embedding video
Week 11
Week 12